## Comm Plan Template
Project: SPM Communication Plan
Recipients | Type of Communication | Frequency | Sender/Owner | Key Dates | Delivery Method | Goal | Resource Links | Notes
CEO | Status Update | Weekly | Project Manager | Every Monday at 2 PM | In Person | Keep informed on project status and high-level decisions | [link to project status] | Prepare a brief update before each meeting.
International VP | Status Update | Weekly | Project Manager | Every Wednesday at 2 PM | In Person/Email | Provide updates and address any concerns | [link to project updates] | Ensure to highlight any strategic decisions needed.
Senior Projects Director | Project Update | Weekly | Project Manager | Every other Friday | In Person/Email | Keep informed on project progress and address potential issues | [link to project milestones] | Communicate challenges early to seek support.
Technical Director | Technical reviews | Weekly | Project Manager | Every other Tuesday | In Person/Email | Discuss technical challenges and solutions | [link to technical reviews] | Focus on ensuring technical feasibility.
Development Director | Daily Stand-Up | Daily | Project Manager | Every day at 10 AM | In Person | Daily updates and feedback on development | [link to daily agenda] | Address any roadblocks quickly.
Infrastructure Senior Manager | Status Update | Daily | Project Manager | Every day at 3 PM | In Person | Ensure infrastructure readiness for the project | [link to infrastructure plans] | Keep in close communication for feedback.
Financial Director | Financial updates | Monthly | Project Manager | First Tuesday of each month | In Person/Email | Discuss budget and financial health of the project | [link to budget report] | Prepare financial updates ahead of meetings.
HR Director | HR Program Update | Weekly | Core Team: HR Specialist | Every Thursday | Email | Update on HR programs and training needs | [link to HR program updates] | Address any resource needs promptly.
Facilities Director | Facility Planning Meeting | Weekly | Project Manager | Every Tuesday | Phone Call | Ensure facilities are ready for the project | [link to facility plans] | Discuss any logistical issues.
Core Team | Planning Meeting | Daily | Core Team: HR Specialist & Training Manager | Every day at 3 PM | In Person | Project planning and task updates | [link to meeting agenda and notes] | Check in with manager about any high-level questions.
HVAC Power Department | Technical Coordination | Daily | Project Manager | Daily at 11 AM | In Person | Coordinate on HVAC installations and operations | [link to HVAC plans] | Quick feedback loop for any issues.
International Partners & Investors | Progress Update | Monthly | Project Manager | Last Friday of each month | Email | Keep informed on project status and performance | [link to performance reports] | Highlight successes and milestones.
Employees | Informational Update | Weekly | Core Team: HR Specialist | Every Friday | Email | Update on project impact on employees | [link to employee updates] | Ensure clear communication regarding changes.
International Customers | Project Update | Quarterly | Core Team: HR Specialist | End of each quarter | Email | Update on project impacts and improvements | [link to customer updates] | Focus on customer benefits from the project.
HR Development Department | Project Collaboration | Weekly | Core Team: HR Specialist | Every Thursday | In Person | Collaborate on training and development initiatives | [link to HR resources] | Ensure training needs are met.
CLS Operation Department | Project Execution Update | Daily | Project Manager | Daily at 10 AM | In Person | Ensure smooth execution of PUE measurements | [link to operation updates] | Ensure training needs are met.
Facility Operation Department | Operational Readiness Update | Daily | Project Manager | Daily at 2 PM | In Person | Discuss employee movement and facility readiness | [link to facility operations] | Keep communication open for any urgent needs.
International Relationship Manager | Project Monitoring | Weekly | Project Manager | Every other Wednesday | Email | Monitor international relationships and updates | [link to relationship updates] | Keep updated on international dynamics.

## Comm Plan Template 2 (hidden)
Project Communication Plan
Project Title:
Project Manager:
Executive Sponsor:
Principal Stakeholder:
Date:
Deliverable Info (What) | Recipient(s) (Who) | Delivery Method(s) (How) | Schedule (When) | Who's Responsible? (Owner)
Project Information
Project Status
Agenda Minutes
Timeline Update
Project Updates Action Item Status
Project Risks

## Comm Plan Template 3 (hidden)
| Purpose | Medium | Frequency | Audience
Kickoff meeting
Project team meetings
Check-ins/ meeting recap
Project status meetings
UX design reviews