## Exemplar Gantt Chart
Gantt Chart
TITLE: SPM (Sustainable project Management) | [6 empty] | COMPANY NAME: |  |  |  |  | Telecom Egypt
PROJECT MANAGER: Shereen Eltayeb | [6 empty] | CREATION DATE: |  |  |  |  | 01/01/2025
TASK ID NUMBER | MILESTONES & TASKS | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [29 empty] | PHASE TWO | [14 empty] | PHASE THREE | [29 empty] | phase four
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15 |  |  |  |  | WEEK 16 |  |  |  |  | WEEK 17 |  |  |  |  | WEEK 18 |  |  |  |  | WEEK 19 |  |  |  |  | WEEK 20 |  |  |  |  | WEEK 21
[7 empty] | JAN | [22 empty] | FEB | [21 empty] | MAR | [20 empty] | APRIL | [8 empty] | MAY | [22 empty] | JUNE
[7 empty] | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R | S | M | T | W | R
1 | REPLACEMENT HVAC | [5 empty] | 1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12 | 15 | 16 | 17 | 18 | 19 | 22 | 23 | 24 | 25 | 26 | 29 | 30 | 31 | 1 | 2 | 5 | 6 | 7 | 8 | 9 | 12 | 13 | 14 | 15 | 16 | 19 | 20 | 21 | 22 | 23 | 26 | 27 | 28 | 29 | 30 | 3 | 4 | 5 | 6 | 7 | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21 | 24 | 25 | 26 | 27 | 28 | 31 | 1 | 2 | 3 | 4 | 7 | 8 | 9 | 10 | 11 | 1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12 | 15 | 16 | 17 | 18 | 19 | 22 | 23 | 24 | 25 | 26 | 29 | 30 | 31 | 1 | 2 | 5 | 6 | 7 | 8 | 9
1.1 | 1.1CUERRENT SYSTEM ASSESSMENT | HVAC power Department | 2024-01-01 | 2024-01-12 | 2 | 0% | bar: JAN S 1 to JAN R 12
1.2 | 1.2 Purchase Equipment | HVAC power Department | 2024-01-15 | 2024-03-15 | 8 | 0% | bar: JAN S 15 to MAR S 10
1.3 | 1.3 HAVAC Installation | HVAC power Department | 2024-03-11 | 2024-04-15 | 4 | 0% | bar: MAR M 11 to APRIL R 4
2 | REPLACEMENT OF OFFICES TO BETTER CONDITIONS
2.1 | 2.1SURVEY THE TEAMS REPLACEMENT | Facility Department | 2024-01-29 | 2024-02-09 | 2 | 0% | bar: JAN S 29 to FEB R 9
2.2 | 2.2 FURNITURE SECOND FLOOR | Facility Department | 2024-02-12 | 2024-04-04 | 8 | 0% | bar: FEB S 12 to APRIL R 4
3 | DEVELOPMENT AND TRAINING FOR SUPERVISORY POSITIONS
3.1 | 3.1TRAINING CONTENT PREPARATION | HR Department | 2024-02-16 | 2024-02-29 | 2 | 0% | bar: FEB R 16 to FEB W 29
3.2 | 3.2TRAINING | HR Development Department | 2024-03-03 | 2024-05-08 | 7 | 0% | bar: MAR S 3 to MAY S 8
4 | Utilization to PUE Matrics
3.1 | 4.1TRAINING CONTENT PREPARATION | CLS Department | 2024-04-07 | 2024-05-12 | 3 | 0% | bar: APRIL S 7 to MAY R 12
3.2 | 4.2TRAINING | CLS Department | 2024-05-15 | 2024-06-09 | 4 | 0% | bar: MAY S 15 to JUNE R 9